## Subject to Approval Projects
CURRENT PROJECTS SUBJECT TO APPROVAL |  | MILESTONES | [13 empty] | DETAILS
PROJECT NAME | DESCRIPTION | PRESENTED TO BOARD | RETAINER SIGNED | RETAINER FUNDED | CONDITION STUDY | FINAL PLAN/IMPACT | BUDGET | PLANNING | PPLD IA | PPLD | BOCC | SEWCD | SCHOOL DISTRICT | CITY COUNCIL | Dev agreement Signed | NOTES
HANCOCK COMMONS | Attainable Housing w/Commercial S/E | 2021-04-01 | 2021-05-01 | 2021-05-01 | 2021-06-01 | 2021-08-21 | 2022-10-22 | 2022-12-22 | 2022-10-22 | 2022-10-22 | 2022-12-22 | 2023-01-23 | 2022-06-22 | Jan/23 Feb/23 | TBD | Dealing with a CMR's issue with project and PPRTA
WEIDNER / CITYGATE | Market Rate Housing w/Commercial Downtown | 2021-04-01 | 2021-06-01 | 2021-07-01 | 2021-09-21 | 2021-11-21 | 2022-10-22 | 2022-11-22 | 2022-10-22 | 2022-12-22 | 2022-05-22 | 2023-01-23 | 2022-05-22 | 2023-03-14 | June | Waiting on signed agreement
GAZETTE SF | Market Rate Housing w/Commercial Downtown | 2021-04-01 | [13 empty] | No New Updates
Gold Hill Commerical | Commercial/Residential development in GHM | 2021-08-21 | 2022-12-21 | 2022-12-21 | 2022-02-22 | 2022-04-22 | 2022-11-22 | 2023-02-23 | 2022-10-22 | 2022-11-22 | 2022-02-23 | 2022-01-23 | 2022-12-22 | Fall |  | Pushed to Fall
Park Union | Boundary expansion and new area | 2022-12-21 | 2022-02-21 | 2021-01-01 | 2022-02-22 | [10 empty] | No New updates
Oneil Project | Office/residential project with retail | 2022-10-21 | 2022-12-21 | 2022-08-22 | 2022-08-22 | [10 empty] | No New updates
Lowell Draper | Downtown attainable housing project | 2022-07-22 | [13 empty] | No New Updates
Project Garnet |  | 2023-01-23 |  |  | 2023-12-22 | 2023-12-22 | N/A | 2023-01-23 | N/A | N/A | 2023-02-23 | 2023-01-23 | 2023-02-23 | 2023-02-23 | May | Waiting on signed agreement

## Current Projects
URA | PROJECT | START | END |  | CONSTRUCTION | PROJECT COMPLETION | NOTES
C4C PROJECTS | AFA Visitor Center |  |  | In Progress | Started | 2024 | Construction is Commenced
| Robson Arena |  |  | Complete | Complete | Complete
| Weidner Field |  |  | Complete | Complete | Complete
| USOPM |  |  | Complete | Complete | Complete
| Hybyl Sports Medicine |  |  | Complete | Complete | Complete
MUSEUM & PARK | Residential & Commercial | 2018 | 2043 | Bonds Issued | Infrastructure/Streetscape | TBD | Developer Proceeding with a New Area/Clock. Streetscape/Bridge won the ULI impact reward
CITY AUD BLOCK | Hyatt Hotel | 2004 | 2029 | Complete | OPEN! | Fall 2021 | Transit center was discussed at Feb 2023 Council meeting. I expect more URA involvement over coming year.
GOLD HILL MESA | Residential | 2004 | 2029 | Complete | In Progress | Fall 2021 | Amendment to boundary area in front of districts as they approve commercial
| Commercial | 2015 | 2040 | No | In Progress | TBD | Expect to finalize through Council March 14
IVYWILD |  | 2011 | 2036 | Complete | Complete | Complete*
N. NEVADA AVE |  | 2015 | 2040 | Complete | Complete* | Complete* | Construction on Lexus Dealership is underway
POLARIS POINTE |  | 2010 | 2035 | Complete | In Progress | Fall 2021/Spring 2022 | Amplitheater passes Council
TEJON & COSTILLA |  | 2018 | 2043 | Complete | In Progress | Spring 2022 | Opened and doing great!
TRUE NORTH COMMONS |  | 2019 | 2044 | No (see AFA) | In Progress | TBD | Under Construction
VINEYARD |  | 2011 | 2036 | Complete | Complete* | Complete* | Closing postponed again.
S. NEVADA | EVC-HD |  |  | Complete | Complete | Complete | Developer has shown interest in securing other sites on east side if TIF available.
| Ivywild LLC |  |  | Complete | In Progress | Late 2024 (estimated) | Have met with Hotel team to discuss new timelines
| Canyon Creek LLC |  |  | Ongoing | In Progress | Late 2024 (estimated) | Council passed sales tax increase to 2% Heavy site work and creek work Danny is working on adding in apartments with new metro district
Almagre |  | 2021 | 2046 | No | In Progress | Summer 2024